RHODONITE

COMPANY PROFILE
QUOTATION

Company Profile Content & Design Development

| PREPARED FOR | Tajir Holding |
| --- | --- |
| PREPARED BY | Rhodonite |
| ENGAGEMENT | Company Profile Content & Design Development |
| COMMERCIAL MODEL | Fixed project fee — 60% advance / 40% on delivery |
| DELIVERY TIMEFRAME | 7 to 10 working days |
| QUOTATION DATE | 02 October 2026 |

COMMERCIAL SUMMARY

ETB 60,000

Before VAT  •  VAT 15%: ETB 9,000  •  Total project value: ETB 69,000 incl. VAT

1. Scope of Work

Rhodonite will develop Tajir Holding’s company profile end to end — from structuring and writing the content to designing a polished, brand-aligned document that presents the group’s identity, portfolio and capabilities to partners, investors and clients.

| 60K | 15% | 60% | 40% | 7–10 |
| --- | --- | --- | --- | --- |
| ETB fee before VAT | VAT applied | Advance payment | Balance on delivery | Working days |

Scope included in the project fee

| SERVICE | INCLUDED RESPONSIBILITY |
| --- | --- |
| Discovery & brief | Kick-off session to confirm objectives, audience, tone and key messages; review of existing materials and brand assets. |
| Content structure | Page flow covering overview, vision, mission & values, leadership message, business units, capabilities, milestones and contacts. |
| Copywriting & editing | Professional English copywriting and editing of all sections in a confident corporate tone, based on information supplied. |
| Design & layout | Cover, visual direction and full page layouts aligned with Tajir Holding’s brand — typography, colour, icons, infographics and imagery. |
| Revisions | Up to two consolidated revision rounds on content and design. |
| Final delivery | Print-ready high-resolution PDF and an optimized digital PDF for email and web. |

Indicative delivery schedule

| TIMELINE | ACTIVITY |
| --- | --- |
| Days 1–2 | Kick-off, content brief, information gathering and content outline approval. |
| Days 3–5 | Copywriting and first design draft (cover, visual direction and full page layouts). |
| Days 6–8 | Consolidated client feedback and revision rounds on content and design. |
| Days 9–10 | Final proofreading, artwork finalization and delivery of final files. |

Timeframe starts upon receipt of the advance payment and the required content inputs.

Client responsibilities

•  Provide company information, business unit details, key figures and any existing profile material.

•  Provide brand assets (logo, guidelines) and approved photographs of projects, facilities and leadership.

•  Assign one focal person for consolidated feedback and approvals within one to two working days.

Not included in the project fee

•  Printing and binding; professional photography, videography or drone shoots.

•  Paid stock images, translation into additional languages, new brand-identity or website development.

2. Professional Fee & Payment Terms

| DESCRIPTION | QTY | UNIT FEE | TOTAL |
| --- | --- | --- | --- |
| Company profile content & design development | 1 project | ETB 60,000 | ETB 60,000 |
| VAT (15%) |  |  | ETB 9,000 |
| TOTAL PROJECT VALUE |  |  | ETB 69,000 |

Payment schedule

| MILESTONE | FEE (BEFORE VAT) | VAT 15% | AMOUNT PAYABLE |
| --- | --- | --- | --- |
| 60% Advance | 36,000 | 5,400 | 41,400 ETB |
| 40% Balance | 24,000 | 3,600 | 27,600 ETB |
| Total | 60,000 | 9,000 | 69,000 ETB |

Payment terms

•  60% advance payment (ETB 36,000 + VAT = ETB 41,400) is due upon acceptance of this quotation; work commences upon receipt of the advance.

•  The remaining 40% balance (ETB 24,000 + VAT = ETB 27,600) is due upon final approval and before handover of the final files.

•  The quoted professional fee is ETB 60,000 before VAT. Ethiopia’s standard 15% VAT is added to each invoice where applicable.

•  Delays in client inputs or approvals may shift the delivery date without affecting the agreed fee.

•  Any work outside the agreed scope will be estimated and approved separately before execution.

Commercial conditions

•  Revisions: up to two consolidated revision rounds; additional rounds or major changes in direction after approval may require re-scoping.

•  Approval window: Tajir Holding should provide consolidated feedback within one to two working days where possible.

•  Ownership: final approved files are handed over to Tajir Holding upon full settlement of the project fee.

•  Quotation validity: 15 calendar days from the quotation date.

Acceptance

| FOR TAJIR HOLDING | FOR RHODONITE |
| --- | --- |
| Name / Title: ______________________________ Signature: __________________________________ | Name / Title: ______________________________ Signature: __________________________________ |
| Date: ______________________________________ | Date: ______________________________________ |